## ToolTracker
Region | BBTName | BBT - Tool Lead (primary contact) | BBT - Overall Lead (secondary contact) | Wpnumber | Task | ToolFamily | ToolName | ToolLead | Application | Testing deadline | Deadline comments | Testing comments | Testing status | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Arctic | North Spitsbergen | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | Jan-Marcin Weslawski | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel | Yes
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes | Completed |  | Completed, waiting for instructions on paper | Completed
Atlantic | Belgium coast - Dogger Bank | VLIZ, Willem Boone, willem.boone@vliz.be; hanneloor.heynderickx@vliz.be | Hanneloor Heynderickx | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel | Yes |  |  |  |  | 2024-12-01: Stakeholder Workshop held
|  |  |  | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel | Yes
Med | Menorca Channel (Balearic islands) | Hilmar Hinz | Silvia de Juan, Hillmar Hinz | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel | Yes |  |  | working
|  |  |  | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel | Yes
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván |  | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel | Yes |  |  | Investigating Cefas benthic data for comparison/validation | In progress
Baltic | Finnish Archipelago | TBD (Tiina Salo, ABO, tsalo@abo.fi) |  | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes | Completed |  | Completed, waiting for instructions on paper | Completed
Baltic | Gulf of Gdansk | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Eleni Koumpaki, e.koumpaki@hcmr.gr | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes |  |  | 2nd round completed, waiting for the 3rd round and further instructions | Waiting for instructions
Atlantic | Irish Sea (Liverpool - Dublin Bay) |  |  | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes | Completed |  |  | Completed
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP1 |  | Other | Structured stakeholder interviews | HUFOSS - Herman Hummel, herman.hummel@hufoss.nl | Yes
Atlantic | Irish Sea (Liverpool - Dublin Bay) | John Aldridge | Dorota Kolbuk | WP3 | T3.1b | Ecological | Biogeochemical modelling | Cefas - John Aldridge, john.aldridge@cefas.gov.uk, | Yes |  |  |  | In progress
Med | Gulf of Heraklion | HCMR, Panagiotis Kasapidis, kasapidi@hcmr.gr | Constantinos Frangoulis, cfrangoulis@hcmr.gr | WP3 | T3.1b | Ecological | Biogeochemical modelling | Cefas - John Aldridge, john.aldridge@cefas.gov.uk, | Yes | Completed |  |  | Completed
Baltic | Curonian lagoon - Lithuanian coast | Burak Kaynaroglu | Jūratė Lesutienė | WP3 | T3.1b | Ecological | Biogeochemical modelling | Cefas - John Aldridge, john.aldridge@cefas.gov.uk, | Yes |  |  | Working; Paper bublished | In progress
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes | Completed |  | results submitted | Completed | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Arctic | South Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Maria Wlodarska | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  |  |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  | working 1 month left |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  |  |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Arctic | North Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Jan-Marcin Weslawski | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  |  |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Med | Menorca Channel (Balearic islands) | Hilmar Hinz | Silvia de Juan, Hillmar Hinz | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  | Completed |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Julie Bremner, Clement Garcia, Dorota Kolbuk | Dorota Kolbuk | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes | Completed |  | Completed | Completed | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Georgios Chatzigeorgiou, chatzigeorgiou@hcmr.gr | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  | inclusion of BBT12 data in an announcement at ICES Conference | completed (activity 1), waiting for further instructions | Waiting for instructions | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Baltic | Gulf of Gdansk | Jan Marcin Weslawski weslaw@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  |  |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Baltic | Finnish Archipelago | Tiina Salo (ABO, tsalo@abo.fi), Anna Törnroos-Remes (ABO, anna.m.tornroos@abo.fi) | Tiina Salo, Marie Nordström | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes | Completed |  | Completed | Completed | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes | Completed |  | Completed | Completed | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 2)
Atlantic | Belgium coast - Dogger Bank | VLIZ, Hanneloor Heynderickx, hanneloor.heynderickx@vliz.be ; Nelle Meyers, nelle.meyers@vliz.be | Klaas Deneudt | WP3 | T3.2b | Ecological | Broadscale trait-based approaches | ABO - Anna Törnroos, anna.m.tornroos@abo.fi | Yes |  |  |  |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Data collection & analysis; 2024-10-01: Data collection & analysis; 2024-11-01: DL: Submission of analysis Nov 30 (Activity 1); 2025-01-01: DL: analysis and data submission Jan 31st (Activity 1); 2025-05-01: Start activity 2; 2025-08-01: deadline
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.2b | Ecological | Causal paths - Bayesian Belief Network (BBN) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | not yet started | Waiting for instructions
Med | Menorca Channel (Balearic islands) | Andres Ospina-Alvarez | Silvia de Juan, Hillmar Hinz | WP3 | T3.2b | Ecological | Causal paths - Bayesian Belief Network (BBN) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | working
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Clement Garcia | Dorota Kolbuk | WP3 | T3.2b | Ecological | Causal paths - Bayesian Belief Network (BBN) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | waiting for info from Clement | In progress
Baltic | Finnish Archipelago | Tiina Salo (ABO, tsalo@abo.fi), Marie Nordström (Univ. Helsinki, marie.nordstrom@helsinki.fi) | Tiina Salo, Marie Nordström | WP3 | T3.2b | Ecological | Causal paths - Bayesian Belief Network (BBN) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | Waiting for instructions | Waiting for instructions
Atlantic | Belgium coast - Dogger Bank | VLIZ, Hanneloor Heynderickx, hanneloor.heynderickx@vliz.be ; Nelle Meyers, nelle.meyers@vliz.be | Klaas Deneudt | WP3 | T3.2b | Ecological | Causal paths - Bayesian Belief Network (BBN) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.3c | Ecological | Causal paths - Structural Equation Modelling (SEM) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | not yet started | Waiting for instructions
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Clement Garcia | Dorota Kolbuk | WP3 | T3.3c | Ecological | Causal paths - Structural Equation Modelling (SEM) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | waiting for info from Clement | In progress
Baltic | Finnish Archipelago | Tiina Salo (ABO, tsalo@abo.fi), Marie Nordström (Univ. Helsinki, marie.nordstrom@helsinki.fi) | Tiina Salo, Marie Nordström | WP3 | T3.3c | Ecological | Causal paths - Structural Equation Modelling (SEM) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | Waiting for instructions | Waiting for instructions
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  | waiting for guidance | In progress
Arctic | South Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Maria Wlodarska | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  | working
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes
Arctic | North Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Jan-Marcin Weslawski | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes
Med | Menorca Channel (Balearic islands) | Andres Ospina-Alvarez | Silvia de Juan, Hillmar Hinz | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  | working
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  |  | Waiting for instructions
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Georgios Chatzigeorgiou, chatzigeorgiou@hcmr.gr | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Maybe |  |  | not sure, not started yet | Not Started
Baltic | Gulf of Gdansk | Jan Marcin Weslawski weslaw@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes
Baltic | Finnish Archipelago | Marie Nordström (Univ. Helsinki, marie.nordstrom@helsinki.fi) | Tiina Salo, Marie Nordström | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  | Ongoing | In progress
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  | Working | Waiting for instructions
Atlantic | Belgium coast - Dogger Bank | VLIZ, Hanneloor Heynderickx, hanneloor.heynderickx@vliz.be ; Nelle Meyers, nelle.meyers@vliz.be | Klaas Deneudt | WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | University of Helsinki - Marie Nordström, marie.nordstrom@helsinki.fi | Yes |  |  |  |  | 2024-11-01: Data collection & analysis; 2024-12-01: Data collection & analysis; 2025-01-01: Data collection & analysis; 2025-02-01: Data collection & analysis; 2025-03-01: Data collection & analysis; 2025-04-01: Data collection & analysis; 2025-05-01: Data collection & analysis
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.3a | Ecological | Ecological vulnerability appraisal | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | not yet started | Waiting for instructions
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP3 | T3.3a | Ecological | Ecological vulnerability appraisal | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  |  | Waiting for instructions
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Georgios Chatzigeorgiou, chatzigeorgiou@hcmr.gr | WP3 | T3.3a | Ecological | Ecological vulnerability appraisal | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  |  | Not Started
Baltic | Finnish Archipelago | Tiina Salo (ABO, tsalo@abo.fi), Marie Nordström (Univ. Helsinki, marie.nordstrom@helsinki.fi) | Tiina Salo, Marie Nordström | WP3 | T3.3a | Ecological | Ecological vulnerability appraisal | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | Waiting for isntructions | Waiting for instructions
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP3 | T3.3a | Ecological | Ecological vulnerability appraisal | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes | - |  | On hold | Cancelled
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes | Completed |  | work in progress | Completed
Arctic | South Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Maria Wlodarska | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes |  |  | need more guidance resources allocated
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes
Arctic | North Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Jan-Marcin Weslawski | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes
Med | Menorca Channel (Balearic islands) | Silvia de Juan | Silvia de Juan, Hillmar Hinz | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes |  |  | Completed
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes |  |  |  | In progress
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Georgios Chatzigeorgiou, chatzigeorgiou@hcmr.gr | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes | end of June |  | completed, waiting for further instructions | Waiting for instructions
Baltic | Gulf of Gdansk | Jan Marcin Weslawski weslaw@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes
Baltic | Finnish Archipelago | Tiina Salo, Anna Törnroos-Remes | Tiina Salo, Marie Nordström | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes | Completed |  | work in progress | Completed
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes | 2025-06-01 |  | Working - progress | In progress
Atlantic | Belgium coast - Dogger Bank | VLIZ, Hanneloor Heynderickx, hanneloor.heynderickx@vliz.be ; Nelle Meyers, nelle.meyers@vliz.be | Klaas Deneudt | WP3 | T3.2c | Ecological | Metric of habitat function | CSIC - Silvia de Juan, silvia.dejuan@csic.es | Yes |  |  |  |  | 2025-05-01: planning to start activity; 2025-09-01: deadline
Atlantic | Southern Gulf of Biscay | Begoña Sánchez, Araceli Puente | Araceli Puente | WP3 | T3.4b | Ecological | Molecular - metabarcoding/eDNA | UCD & HCMR - Nettan Carlsson, jeanette.carlsson@ucd.ie, Jens Carlsson jens.carlsson@ucd.ie, Panagiotis Kasapidis, kasapidi@hcmr.gr | Yes |  |  | no instructions | Waiting for instructions
Med | Menorca Channel (Balearic islands) | Silvia de Juan | Silvia de Juan, Hillmar Hinz | WP3 | T3.4b | Ecological | Molecular - metabarcoding/eDNA | UCD & HCMR - Nettan Carlsson, jeanette.carlsson@ucd.ie, Jens Carlsson jens.carlsson@ucd.ie, Panagiotis Kasapidis, kasapidi@hcmr.gr | Yes |  |  | Data analysed (data available at 20 sites from previous projects + MARBEFES)
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Nettan Carlsson, Jens Carlsson | Dorota Kolbuk | WP3 | T3.4b | Ecological | Molecular - metabarcoding/eDNA | UCD & HCMR - Nettan Carlsson, jeanette.carlsson@ucd.ie, Jens Carlsson jens.carlsson@ucd.ie, Panagiotis Kasapidis, kasapidi@hcmr.gr | Yes |  |  | In progress | In progress
Med | Gulf of Heraklion | HCMR, Panagiotis Kasapidis, kasapidi@hcmr.gr |  | WP3 | T3.4b | Ecological | Molecular - metabarcoding/eDNA | UCD & HCMR - Nettan Carlsson, jeanette.carlsson@ucd.ie, Jens Carlsson jens.carlsson@ucd.ie, Panagiotis Kasapidis, kasapidi@hcmr.gr | Yes |  |  |  | In progress
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP3 | T3.4b | Ecological | Molecular - telomeres | APN - Sabine Cochrane, skc@akvaplan.niva.no | yes |  |  | analysis in progress report planned
Baltic | Finnish Archipelago | Marie Nordström, | Tiina Salo, Marie Nordström | WP3 | T3.3c | Ecological | PlanWise4Blue (PW4B) | UT - Jonne Kotta, bluebiosites@ut.ee | Yes |  |  | Ongoing | Waiting for instructions
Atlantic | Southern Gulf of Biscay | Xabier Guinda, Elvira Ramos | Araceli Puente | WP3 | T3.4a | Ecological | Remote sensing decision tree | CSIC - Hilmar Hinz, hhinz@imedea.uib-csic.es | Yes | Completed |  | completed the online survey | Completed
Med | Menorca Channel (Balearic islands) | Hilmar Hinz | Silvia de Juan, Hillmar Hinz | WP3 | T3.4a | Ecological | Remote sensing decision tree | CSIC - Hilmar Hinz, hhinz@imedea.uib-csic.es | Yes |  |  | working
Baltic | Finnish Archipelago | Marie Nordström marie.nordstrom@helsinki.fi Tiina Salo (ABO, tsalo@abo.fi) | Tiina Salo, Marie Nordström | WP3 | T3.4a | Ecological | Remote sensing decision tree | CSIC - Hilmar Hinz, hhinz@imedea.uib-csic.es | Yes |  |  | Ongoing | In progress
Baltic | Finnish Archipelago | Tiina Salo (tsalo@abo.fi | Tiina Salo tsalo@abo.fi | WP3 | T3.3b | Ecological | The viability of indicators of functional change | CNR Paolo Magni | Yes |  |  | in progress | Waiting for instructions
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP3 | T3.3b | Ecological | The viability of indicators of functional change | CNR Paolo Magni | Yes |  |  | in progress | In progress
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP3 | T3.3b | Ecological | The viability of indicators of functional change | CNR Paolo Magni | Yes
Med | Gulf of Heraklion | HCMR, Panagiotis Kasapidis, kasapidi@hcmr.gr | Ioannis Tsakalakis, I.tsakalakis@hcmr.gr | WP3 | T3.3b | Ecological | The viability of indicators of functional change | CNR Paolo Magni | No |  | T3.3b is a knowledge-generation exercise rather than tool development, so it takes place solely within WP3 without testing in WP2.
Med | Menorca Channel (Balearic islands) | Hilmar Hinz | Silvia de Juan, Hillmar Hinz | WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | No
Med | Gulf of Heraklion | HCMR, Panagiotis Kasapidis, kasapidi@hcmr.gr | Constantinos Frangoulis, cfrangoulis@hcmr.gr | WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes | Completed |  | completed | Completed
Baltic | Finnish Archipelago | TBD (Tiina Salo, ABO, tsalo@abo.fi) | Tiina Salo, Marie Nordström | WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | No | - |  |  | Cancelled
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  | Working | In progress
Atlantic | Belgium coast - Dogger Bank | VLIZ, Hanneloor Heynderickx, hanneloor.heynderickx@vliz.be | Klaas Deneudt | WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes
Med | Gulf of Heraklion | HCMR, Panagiotis Kasapidis, kasapidi@hcmr.gr | Niki Keklikoglou (keklikoglou@hcmr.gr) | WP3 | T3.4c | Ecological | Traits - micro computer tomography (micro-CT) | HCMR - Niki Keklikoglou, keklikoglou@hcmr.gr | Yes | Completed | A case study from BBT12: 2 marine invertebrates were visualized through micro-CT and several morphological traits were derived, data for the deliverable submitted by 30th of September has already been uploaded to MDA | completed | Completed
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 |  | Economic | BEACH Tool (Benefit Evaluation through Assessment of Component Habitats) | IECS - Daryl Burdon, daryl.burdon@iecs.ltd | Maybe |  |  | not yet started | Not Started
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Clement Garcia | Dorota Kolbuk | WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Cefas - Clement Garcia, clement.garcia@cefas.gov.uk | Yes |  |  |  | In progress
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Daryl Burdon, Steve Barnard | Dorota Kolbuk | WP4 |  | Economic | BEACH Tool (Benefit Evaluation through Assessment of Component Habitats) | IECS - Daryl Burdon, daryl.burdon@iecs.ltd | Yes |  |  | tool ready to test, data sets are being prepared | In progress
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 |  | Economic | Benefit/value transfer | UNITN - Carlo Fezzi, carlo.fezzi@unitn.it | Maybe |  |  | not yet started | Not Started
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 | T4.3c | Economic | Complementary Accounting Network (CAN) | UEA - Kerry Turner, r.k.turner@uea.ac.uk | Maybe |  |  | not yet started | Not Started
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Ashley Cahillane | Dorota Kolbuk | WP4 | T4.2b | Cultural | Cultural representations analysis | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  |  | In progress
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Bárbara Ondiviela | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). | done | Completed
Arctic | South Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Maria Wlodarska | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing).
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). | completed. 4-5 components
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing).
Arctic | North Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Jan-Marcin Weslawski | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing).
Med | Menorca Channel (Balearic islands) | Silvia de Juan | Silvia de Juan, Hillmar Hinz | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). | Completed
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). |  | Completed
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Georgios Chatzigeorgiou, chatzigeorgiou@hcmr.gr | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). | waiting for further instructions | Waiting for instructions
Baltic | Gulf of Gdansk | Aleksandra Koroza akoroza@iopan.pl | JMW, Joanna Piwowarczyk | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing).
Baltic | Finnish Archipelago | Tiina Salo (ABO, tsalo@abo.fi) | Tiina Salo, Marie Nordström | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). | Completed | Completed
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). | Still working - second revision | In progress
Atlantic | Belgium coast - Dogger Bank | VLIZ, Willem Boone, willem.boone@vliz.be; hanneloor.heynderickx@vliz.be | Hanneloor Heynderickx | WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | IECS - Anita Franco, Anita.Franco@iecs.ltd | Yes | 2025-06-01 | Testing by BBTs (WP2) was originally scheduled to run in the second year (months 13-24), for the revision of the EVA guidance (WP4) to then be undertaken in the third year (months 25-34). In the end, the two activities were run in parallel, with final deadline in month 34 (June 2025) to allow time for all BBTs to gather the data and complete the testing, while gathering feedback from them during the proceedings so that the EVA methodology could be revised in 'real time' (e.g., errors corrected, procedures streamlined) and the amended/updated/improved protocol fed back to the BBTs for implementation (within reason, considering the timeline of the testing). |  |  | 2024-06-01: Data collection & analysis; 2024-07-01: Data collection & analysis; 2024-08-01: Data collection & analysis; 2024-09-01: Submission EVA results; 2024-10-01: Finished
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Ashley Cahillane | Dorota Kolbuk | WP4 | T4.2b | Cultural | GIS mapping of cultural representations | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  |  | In progress
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 |  | Economic | Hedonic pricing | UNITN - Carlo Fezzi, carlo.fezzi@unitn.it | Maybe |  |  | not yet started | Not Started
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 | T4.3b | Economic | Monetary natural capital accounting | UEA - Silvia Ferrini, s.ferrini@uea.ac.uk | Maybe |  |  | not sure | Completed
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP4 | T4.3b | Economic | Monetary natural capital accounting | UEA - Silvia Ferrini, s.ferrini@uea.ac.uk | Yes
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Valentina Di Gennaro | Dorota Kolbuk | WP4 | T4.3b | Economic | Monetary natural capital accounting | UEA - Silvia Ferrini, s.ferrini@uea.ac.uk | Yes |  |  | fisheries completed, carbon sequestration and recreation in progress | In progress
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  | will not apply | Not Started
Arctic | South Spitsbergen | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | Maria Wlodarska | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  | in process
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  | starting up
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  |  | Completed
Arctic | North Spitsbergen | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | Jan-Marcin Weslawski | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  | in process
Med | Menorca Channel (Balearic islands) |  | Silvia de Juan, Hillmar Hinz | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | 2025-02-25 |  | In progress (5 BBTs finished, 5 BBTs in progress, 1 BBT to start)
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Ashley Cahillane | Dorota Kolbuk | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  |  | Completed
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Eleni Koumpaki, e.koumpaki@hcmr.gr | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | end of September | participation in a joint publication led by Ashley | completed, waiting for further instructions for the publication | Completed
Baltic | Gulf of Gdansk | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  | in process
Baltic | Finnish Archipelago | TBD (Tiina Salo (ABO, tsalo@abo.fi), Marie Nordström (Univ. Helsinki, marie.nordstrom@helsinki.fi) ) | Tiina Salo, Marie Nordström | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes |  |  | Ongoing | In progress | 2025-08-01: questionnaire out; 2025-09-01: questionnaire ends
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | 2025-06-01 |  | Working onsite will be delayed till the end of eptember | In progress
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Ashley Cahillane | Dorota Kolbuk | WP4 | T4.2b | Cultural | Participatory research - interviews, focus groups, and arts-based workshop | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  |  | Completed
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 | T4.2b | Cultural | Participatory research - online surveys | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  | results submitted | Completed
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP4 | T4.2b | Cultural | Participatory research - online surveys | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  |  | Completed
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Ashley Cahillane | Dorota Kolbuk | WP4 | T4.2b | Cultural | Participatory research - online surveys | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  |  | completed
Atlantic | Belgium coast - Dogger Bank | VLIZ, Willem Boone, willem.boone@vliz.be; | Hanneloor Heynderickx | WP4 | T4.2b | Cultural | Participatory research - online surveys | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | Completed |  |  | Completed | 2024-10-01: Data collection & analysis; 2024-11-01: Data collection & analysis; 2024-12-01: Data collection & analysis; 2025-01-01: Data collection & analysis; 2025-02-01: Submission results; 2025-03-01: Finished
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Eleni Koumpaki, e.koumpaki@hcmr.gr | WP4 | T4.2b | Cultural | Participatory research - online surveys | UCD - Ashley Cahillane, ashley.cahillane@ucd.ie | Yes | end of September | participation in a joint publication led by Ashley | completed, waiting for further instructions for the publication | Completed
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Georgios Chatzigeorgiou, chatzigeorgiou@hcmr.gr | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes | end of June |  | completed, waiting for further instructions | Waiting for instructions
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes | Completed |  | 2 approahes results ready | Completed
Arctic | South Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Maria Wlodarska | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes |  |  | working. resources allocated
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes
Arctic | North Spitsbergen | Jan Marcin Weslawski weslaw@iopan.gda.pl | Jan-Marcin Weslawski | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes
Med | Menorca Channel (Balearic islands) | Silvia de Juan | Silvia de Juan, Hillmar Hinz | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes |  |  | Completed
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes | Completed |  |  | Completed
Baltic | Gulf of Gdansk | Aleksandra Koroza akoroza@iopan.pl | JMW, Joanna Piwowarczyk | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes
Baltic | Finnish Archipelago | Tiina Salo (ABO, tsalo@abo.fi), Marie Nordström (Univ. Helsinki, marie.nordstrom@helsinki.fi) | Tiina Salo, Marie Nordström | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes | Completed |  | Completed | Completed
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes | 2025-06-01 |  | On hold till the updated version of EVA | In progress
Atlantic | Belgium coast - Dogger Bank | VLIZ, Willem Boone, willem.boone@vliz.be; | Hanneloor Heynderickx | WP4 | T4.3a | Economic | Physical natural capital accounting | Cefas - Tiziana Luisetti, tiziana.luisetti@cefas.gov.uk | Yes |  |  |  |  | 2025-06-01: Submitred results
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 |  | Economic | Stated preference method | UNITN - Carlo Fezzi, carlo.fezzi@unitn.it | No |  |  | not started | In progress
Atlantic | Southern Gulf of Biscay | Bárbara Ondiviela, Cristina Galván | Bárbara Ondiviela | WP4 |  | Economic | Travel cost method | UNITN - Carlo Fezzi, carlo.fezzi@unitn.it | No |  |  | not started | Not Started
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP4 | T4.2 | Economic | Bebefit Transfer | UNITN - Carlo Fezzi, carlo.fezzi@unitn.it | Yes | Completed |  | Completed, draft is inpreparion for submission | Completed
Baltic | Curonian lagoon - Lithuanian coast | Jūratė Lesutienė | Jūratė Lesutienė | WP4 | T4.2b | Economic | Travel cost method | UNITN - Carlo Fezzi, carlo.fezzi@unitn.it | Yes | Completed |  | Completed, writing the draft now | Completed
Arctic | South Spitsbergen | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | Maria Wlodarska | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
Arctic | North Spitsbergen | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | Jan-Marcin Weslawski | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
Arctic | South Spitsbergen | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | Maria Wlodarska | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes | Completed |  | Completed | Completed
Baltic | Curonian lagoon - Lithuanian coast |  | Jūratė Lesutienė | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 |  | Completed, waiting for instructions on paper | Completed
Atlantic | Belgium coast - Dogger Bank | VLIZ, Willem Boone, willem.boone@vliz.be; hanneloor.heynderickx@vliz.be | Hanneloor Heynderickx | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes |  |  |  |  | 2024-12-01: Data collection & analysis; 2025-01-01: Data collection & analysis; 2025-02-01: Submission results; 2025-03-01: Finished
Atlantic | Belgium coast - Dogger Bank | VLIZ, Willem Boone, willem.boone@vliz.be; hanneloor.heynderickx@vliz.be | Hanneloor Heynderickx | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 |  |  |  | 2024-06-01: Data submitted - Finished
|  |  |  | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
|  |  |  | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30
Med | Menorca Channel (Balearic islands) | Hilmar Hinz | Silvia de Juan, Hillmar Hinz | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes |  |  | waiting instructions
Med | Menorca Channel (Balearic islands) | Hilmar Hinz | Silvia de Juan, Hillmar Hinz | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 |  | Completed
|  |  |  | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
|  |  |  | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes | Completed |  |  | Completed
Atlantic | Southern Gulf of Biscay | Cristina Galván, Elvira Ramos | Araceli Puente | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 |  |  | Completed
Baltic | Finnish Archipelago | TBD (Tiina Salo, ABO, tsalo@abo.fi) |  | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes | Completed |  | Completed | Completed
Baltic | Finnish Archipelago | TBD (Tiina Salo, ABO, tsalo@abo.fi) |  | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 |  | Completed | Completed
Baltic | Gulf of Gdansk | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
Baltic | Gulf of Gdansk | Joanna Piwowarczyk piwowarczyk@iopan.gda.pl | JMW, Joanna Piwowarczyk | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Thanos Dailianis, thanosd@hcmr.gr | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes |  |  | completed, waiting for further instructions | Waiting for instructions
Med | Gulf of Heraklion | HCMR, Yolanda Koulouri, yol72@hcmr.gr | Thanos Dailianis, thanosd@hcmr.gr | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 | submission of a manuscript to RIO journal for BBT12 according to tool developers | completed | Completed
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes | Completed |  |  | Completed
Atlantic | Irish Sea (Liverpool - Dublin Bay) | Dorota Kolbuk | Dorota Kolbuk | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30 |  |  | Completed
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
Med | Oristano, Sardinia | Paolo Magni | Paolo Magni | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP5 | T5.1 | Other | Scenario downscaling | UCD - Tasman Crowe Tasman.crowe@ucd.ie | Yes
Arctic | Porsanger fjord - Barents Sea |  | Sabine Cochrane, Paul Renaud | WP5 |  | Other | Bowtie with DAPSIWRM | IECS - Mike Elliott, mike.elliott@iecs.ltd | Yes | 2024-09-30
Note on H100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Aleksandra Koroza, akoroza@iopan.pl
Note on M106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: working with uni salamanca

## Tool matrix
WP | Task | Tool family | Tool name | Tool type | Purpose | Use in MARBEFES toolbox | Inputs (information requirements) | Outputs | Target users | Stage of development at start of MARBEFES | Where being tested | Notes | Porsanger Fjord | South Spitsbergen | North Spitsbergen | Archipelago Sea | Curonian Lagoon | Gulf of Gdansk | Belgian Coast - Dogger Bank | Irish Sea | Southern Gulf of Biscay | Menorca Channel | Oristano, Sardinia | Gulf of Heraklion
|  | Ecological/environmental/ecosystem, cultural, economic/socio-economic |  |  | Generating/understanding data, supporting decision-making |  | Information, knowledge |  | Researchers, Policy advisors/makers, Practitioners (environmental managers, planners, industry etc), Citizens |  | (All BBTs, Many BBTs, Selected BBTs only)
WP3 | T3.4c | Ecological | Traits - micro computer tomography (micro-CT) | Equipment and protocol | Generating/understanding data | Generate new information on biological traits | Information - biological samples | Images and measurements of organisms | Researchers | Initial development | Selected BBTs only | Only Gulf of Heraklion BBT have this equipment, though they may use samples from other BBTs |  |  |  | NO |  |  |  |  | NO (we can provide samples) | NO |  | ü
WP3 | T3.4c | Ecological | Traits - animal imager (ZooScan) | Equipment and protocol | Generating/understanding data | Generate new information on biological traits | Information - biological samples | Images and measurements of organisms | Researchers | Initial development | Selected BBTs only | BBTs who already have this equipment, though they may include samples from other BBTs. Tool is being developed for benthos, hyperbenthos and plankton |  |  |  | ? | ü |  | ? | ü | NO (we can provide samples) | YES |  | ü
WP3 | T3.4b | Ecological | Molecular - metabarcoding/eDNA | [To be confirmed by tool point of contact] | Generating/understanding data | Generate new information on organism taxonomy and distribution and populations | Information - biological samples | [To be confirmed by tool point of contact] | Researchers, Practitioners, Citizens | Improvement | Selected BBTs only | Selected BBTs only | ü |  |  | Can provide samples |  |  |  | ü | YES | YES | YES (lead by UCD) | ü
WP3 | T3.4b | Ecological | Molecular - telomeres | [To be confirmed by tool point of contact] | Generating/understanding data | Create an indicator of organism stress (impact indicator) | Information - biological samples | [To be confirmed by tool point of contact] | Researchers, Policy advisors/makers | Initial development | Selected BBTs only | Selected BBTs only | ü |  |  | NO |  |  |  |  | NO | NO
WP3 | T3.1b | Ecological | Biogeochemical modelling | Numerical model | Generating/understanding data | To understand biogeochemical/lower trophic level processes and predict response to changes in forcing | Information - data on oeanographic conditions, biogeochemical processes, functional groups | [To be confirmed by tool point of contact] | Researchers, Policymakers | Initial development | Selected BBTs only | Only BBTs that have existing models;At present Irish Sea, Curonian Lagoon, and Adriatic BBTs; there is no expectation for other BBTs to develop biogeochemical models but outputs/knowledge can be made available for comparison or use by geographically similar BBTs. |  |  |  | NO | ü |  |  | ü | NO | NO |  | ü
WP3 | T3.2b | Ecological | Causal paths - Bayesian Belief Network (BBN) | Multivariate statistical analysis | Generating/understanding data | To define and test management scenarios while tracking their effect on ecosystem services change | Information - main known environmental drivers of the ecosystem functions and services of interest | Visualisation of the network, [tool point of contact to confirm what other data produced] | Researchers, Practitioners | Initial development | Many BBTs | Many BBTs | ü |  |  | ü |  |  |  | ü | YES | YES
WP3 | T3.3c | Ecological | Causal paths - Structural Equation Modelling (SEM) | Multivariate statistical analysis | Generating/understanding data | To spatially predict ecosystem functions and links to service based on environmental parameters (coupled with PlanWise4Blue) | Information - spatial layers of the main known environmental drivers of the ecosystem functions and services of interest | [To be confirmed by tool point of contact] | Researchers | Initial development | Many BBTs | Many BBTs |  |  |  | ü |  |  |  | ü | YES | NO
WP3 | T3.3c | Ecological | PlanWise4Blue (PW4B) | Web based and spatially-explicit platform | Supporting decision-making | To model and map nature values (including ecosystem services) and assess the cumulative impact of human activities on marine ecosystems | Information – spatially explicit layers of relevant environmental driver, ecological components (species, habitats) and processes (which define the functioning of ecosystems and flow of services), and human activities/pressures | Data layers and maps (other outputs are possible) that can be toggled to explore the interactions between nature and human activities | Researchers, Policy advisors/makers, Practitioners | Complete | Selected BBTs only | Tool originally developed for the Baltic Sea https://gis.sea.ee/bluebiosites/. Tool can be applied in entirety or only selected modules | ? |  |  | ü |  |  |  |  | YES | NO
WP3 | T3.2b | Ecological | Ecological Interaction Networks – structure and function | Conceptual / mechanistic model | Generating/understanding data | To describe and quantify food web structure (biodiversity) + quantify ecosystem functioning (mechanistic model) | Information – species list, interactions list for biodiversity; species body masses, total biomass, organism functional type, temperature for ecosystem functioning | Visualisation of the network and summary statistics | Researchers | Complete | All BBTs | No expectation of full EINs from all BBTs, but summary information can be produced by all. Guidelines to be completed late October/early November | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü
WP3 | T3.2b | Ecological | Broadscale trait-based approaches | Statistical analysis | Generating/understanding data | To evaluate structural biodiversity (traits) change e.g. between impacted and non-impacted areas, along biodiversity or geographic gradients; to mechanistically assess changes in functions within habitats, BBTs or across regions | Information - abundance/biomass community data (sp x station matrix, sp x trait matrix), environmental data (station x environment matrix) | Various outputs, e.g. trait matrices, trait distributions, trait maps, multivariate analysis data | Researchers, Practitioners | Initial development | All BBTs | This tool represents a group of related activities. Some activities can include all BBTs, others include a few BBTs | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü
WP3 | T3.2c | Ecological | Metric of habitat function | Conceptual model | Generating/understanding data | To estimate ecosystem function in BBTs/seascapes | Information - habitat data, function/traits data (minimum data need: EUNIS habitat maps) | Matrix of key functions per habitat, spatial map of function | Researchers | Complete | All BBTs | Final version of guidelines to be completed in November. Proposed levels 1&2 to be done at all BBTs, levels 3 and 4 at selected levels. | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü
WP3 | T3.4a | Ecological | Remote sensing decision tree | Decision tree | Generating/understanding data | To guide selection of remote sensing tools for survey and monitoring of benthic ecosystem function | Information - survey aims and details of local conditions | Answers on which survey method to use depending on circumstances | Researchers, Practitioners | Initial development | Many BBTs | TBC if task will result in a 'tool'. Users will answer questions posed by the decision tree to identify which technology to use for benthic ecosystem function depending on their circumstances. Will be available for all BBTs to use, as needed, but no expectations on BBTs to use. |  |  |  | ü |  |  |  |  | YES | YES
WP3 | T3.3a | Ecological | Ecological vulnerability appraisal | Analytical process | Generating/understanding data | Adapting climate risk assessments to assess ecological vulnerability at the seascape level. Uses RLQ analysis | Information – environment, species and traits data | tbc by tool developer | Researchers | Initial development | Many BBTs | Further tool activity when tool development lead (Clement Garcia) returns from parental leave in March 2024 | ü | [7 empty] | YES
WP4 | T4.1 | Ecological | Ecological Value Assessment (EVA) | Multimetric index | Generating/understanding data | To identify subzones in the BBT which have higher ecological value | information - evidence on distribution of species groups or habitats in the BBT from e.g. monitoring data (presence/absence or abundance/extent) or data-derived products (e.g. model predictions) Knowledge - expert judgment where information not available | Spatial map of ecological value per grid cell | Researchers, Policy advisors/makers, Practitioners | Complete | All BBTs | Guidance: https://nc-marbefes.iopan.pl/nextcloud/s/YkWC8F3kCsetZ5W | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü
WP4 | T4.2b | Cultural | Participatory mapping of cultural ecosystem services | Web based GIS app | Generating/understanding data | To highlight the cultural ecosystem benefits attached to particular places, and identify trends such as cultural benefit ‘hotspots’ | Knowledge - citizens judgement | Spatial map of distribution of cultural ecosystem services in particular areas. | Researchers, Policy advisors/makers, Practitioners, Citizens | Complete | All BBTs | Does not require expertise in socio-cultural valuation; citizens input data into online database | [8 empty] | YES | YES
WP4 | T4.2b | Cultural | GIS mapping of cultural representations | GIS tool | Generating/understanding data | To explore the number and general characteristics of cultural texts (e.g. films, plays, poems, paintings, novels) which depict cultural ecosystem services in a particular place | Information - online databases of cultural representations | Spatial map of of clusters of cultural representations of particular areas to identity cultural "hotspots" | Researchers, Policy advisors/makers, Practitioners, Citizens | Complete | Selected BBTs only | Does not require expertise in socio-cultural valuation |  |  |  | NO |  |  |  | ü | NO | NO
WP4 | T4.2b | Cultural | Participatory research - online surveys/questionnaire | Interactive activities | Generating/understanding data | To assess the perceived cultural ecosystem services and benefits attached to particular places; to identify perceived hazards, threats, conflicts, and co-benefits connected to ecosystems | Knowledge - citizens judgement | Quantitative and qualitative evidence on [tool point of contact to confirm what the data will be] | Researchers, Policy advisors/makers, Practitioners, Citizens | Improvement | Selected BBTs only | Does not require expertise in socio-cultural valuation |  | ü | ü | NO | ü | ü | ü | ü | YES | NO | ü | ü
WP4 | T4.2b | Cultural | Participatory research - interviews, focus groups, and arts-based workshops | Interactive activities | Generating/understanding data | To assess the perceived cultural ecosystem services and benefits attached to particular places; to identify perceived hazards, threats, conflicts, and co-benefits connected to ecosystems; to identify stakeholders | Knowledge - citizens judgement | Quantitative and qualitative evidence on citizen perceptions | Researchers, Policy advisors/makers, Practitioners, Citizens | Improvement | Selected BBTs only | Requires expertise in socio-cultural valuation |  |  |  | NO |  |  |  | ü | NO | NO
WP4 | T4.2b | Cultural | Cultural representations analysis | Textual and cultural analysis | Generating/understanding data | To analyse the perceived cultural ecosystem services and benefits attached to particular places, especially over longer periods of time | Information - cultural texts and an appropriate reading methodolody (e.g. frameworks of ecocriticism or environmental humanities) | Qualitative evidence on cultural production. | Researchers, Policy advisors/makers, Practitioners, Citizens | Improvement | Selected BBTs only | Requires expertise in socio-cultural valuation |  |  |  | NO |  |  |  | ü | NO | NO
WP4 |  | Economic | Simplified monetary value estimator | Parametrized model | Generating/understanding data | Simplified approach to get an estimate of the monetary value of some ecosystem services (provisioning, regulation, cultural) | Three levels of information quality | Estimates of ecosystem services economic value | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | In process |  | YES | YES | YES |  | YES |  |  | YES | YES
WP4 |  | Economic | Hedonic pricing | Statistical model | Generating/understanding data | To decompose the price of a marketed good (usually real estate property) and identify which part corresponds to its environmental attributes. | Information - database of transactions, including prices and explanatory variables | Data on economic value of environmental goods | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | In process. See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  | NO |  |  |  |  | ? | NO
WP4 |  | Economic | Benefit/value transfer | Meta-analysis model | Generating/understanding data | To estimate the economic value of non-market ecosystem services using alternative site-based data when an original valuation study is not feasible | Information - economic value of ecosystem services at alternative sites; value functions or, at least, value parameters to implement the value adjustment (transfer). | Data on economic value of ecosystem services | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | In process. See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  | NO |  |  |  |  | ? | NO | YES
WP4 | T4.3c | Economic | Complementary Accounting Network (CAN) | Conceptual model | Supporting decision-making | Dashboard of quantitative indicators | Information - ecological/environmental, economic and social data on ecosystem health, SEEA EA, modified SEEA EA, Cultural ecosystem services | Data on monetary value of ecosystem services/benefits | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  | NO | [5 empty] | NO | YES
WP4 |  | Economic | BEACH Tool (Benefit Evaluation through Assessment of Component Habitats) | Matrix | Generating/understanding data | To estimate the monetary value of the societal benefits obtained from habitats | Information - habitat extent (EUNIS level 3); national valuation data for societal benefits | Data on monetary value of societal benefits of habitats | Researchers, Policy advisors/makers, Practitioners | Complete | Selected BBTs only | No modeling expertise is needed; see M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  | NO |  |  |  | ü | ? | NO
WP4 |  | Economic | Stated preference method | Econometric/statistical model | Generating/understanding data | To estimate use and non-use values of environmental goods | Information - respondents willingness to pay (Contingent Valuation) or choices among different scenarios (Discrete Choice Experiments) | Data on economic value of ecosystem benefits | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  | NO |  |  |  |  | ? | NO
WP4 |  | Economic | Travel cost method | Econometric model | Generating/understanding data | To estimate the recreation values and number of visits to different sites in an area under a variety of different management scenarios | Information - locations and characteristics of outdoor recreational sites, number of citizen visits to the sites and distance to their home location | Data on economic value of ecosystem benefits | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  |  | ü |  |  |  | ? | NO
WP4 | T4.3a | Economic | Physical natural capital accounting | Matrices | Generating/understanding data | To value biodiversity and ecosystem services/benefits | Information – ecological and environmental data | Data on habitat extent, habitat condition of ecosystem services/benefits | Researchers, Policy advisors/makers, Practitioners | Improvement | All BBTs | Options are: contacting BC3 to add EVA results in QGIS or ArcGIS or contact Tiziana and Daryl for a simplified version (as in M35 and M39). See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü
WP4 | T4.3b | Economic | Monetary natural capital accounting | Matrices | Generating/understanding data | To value biodiversity and ecosystrem services/benefits | Information - ecological, environmental, economic data | Data on monetary value of ecosystem services/benefits | Researchers, Policy advisors/makers, Practitioners | Improvement | Selected BBTs only | See M35 Guidance Document on Socio-Economic Frameworks and Methods for Application in the BBTs |  |  |  | NO |  |  |  | ü | ? | NO | ü
WP1 |  | Other | Structured surveys | Interactive activities | Generating/understanding data | To identify ecological and socio-economic elements important in the BBTs according to stakeholders | Knowledge - citizens judgement | Aggregated information on the views and priorities of stakeholders about biodiversity, human activities and marine management | Researchers; Practitioners | Complete | All BBTs | All BBTs | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü
WP5 |  | Other | Bow-tie analysis | Conceptual model | Supporting decision-making | To define which problem reduces biodiversity in the BBT and how to solve it (biodiversity storyline development) | Information - projects and literature Knowledge - expert judgement of previous experience | Visualisation of network of key problems, drivers, impacts and solutions | Researchers, Policy advisors/makers, Practitioners | Complete | All BBTs | It is an aspiration that all BBTs will test the Bowtie tool to explore biodiversity scenarios. Guidance: https://nc-marbefes.iopan.pl/nextcloud/s/XrQXF4WFtcsTYC8 Linked to DAPSI(W)R(M) | ü | ü | ü | ü | ü | ü | ü | ü | YES |  | ü | ü
WP5 | T5.1 | Other | Scenario downscaling (using Land2Sea tool) | Matrix | Supporting decision-making | To imagine the changes in biodiversity and ecosystem variables under a range of possible future societal conditions | Information - global scenarios Knowledge - expert and citizen judgement on societal and ecosystem change | Matrix of scores for direction and strength of changes in biodiversity and society variables under different possible futures | Researchers, Policy advisors/makers, Practitioners | Complete | All BBTs | Scenarios (in the MARBEFES context) are a set of narratives that describe how society may look in future; these scenarios are global and need to be localised to BBTs. Examples of variables used and the tool: https://esdecide.shinyapps.io/Land2Sea_DST/ | ü | ü | ü | ü | ü | ü | ü | ü | YES | YES | ü | ü

## Tool matrix notes
Explanation of columns
Column A | WP | Work package developing the tool
Column B | Tool family | Tool grouping as per MARBEFES aims (ecosystem studies, economic and cultural nature valuation, other uses)
Column C | Tool name
Column D | Type | Describes what the tool is (e.g. a matrix, a piece of equipment, a model)
Column E | Purpose | What the tool does (does it generate new understanding of biodiversity/ecosystems, does it support policy/management decision making?)
Column F | Use | What the tool will be used for in the MARBEFES toolbox (e.g. to generate new biodiversity data, to imagine the future, to value ecosystem goods)
Column G | Inputs | What inputs will be needed to run the tool, grouped under knowledge or information
Column H | Outputs | Describes what the tool will produce
Column I | Target users | Who the tool developers expect might use the tool in future
Column J | Development stage | Whether in the early stages, needing some further development or ready to be tested
Column K | Point of contact | Person to contact for each tool (usually the main tool developer)
Column L | Expectations of BBTs | How many BBTs will be expected to test the tools
Column M | Notes | Information to assist BBTs
Columns N-Y | BBT-specific | Which tool will be tested in which BBT
Colour coding
WP1
WP3
WP4
WP5
Ecological
Cultural
Economic
Other

## data
Waiting for instructions
Not Started
In progress
Completed
Completed with deviations
Cancelled